## v1
Website Tasks | Cost | StoryMap Tasks | Cost
Phase 1: Data Preparation \ Content Migration | 65000 | Phase 1: Data Preparation/Update | 55000
Design data architecture (CSV/Markdown) and migrate content from 2025 Bridge Guidebook PDFs |  | Consolidate information in spreadsheets, PPT, and PDFs into fewer files to allow for data checking
Update data as 2025 data becomes available |  | Update data as 2025 data becomes available
QA/QC CSV and Markdown files (No duplicated data across files)
Translate website text to allow for bilingual navigation
Phase 2: Core Development | 55000 | Phase 2: Core Development | 40000
Build scripts for web page and PDF generation (automation) |  | Revise StoryMap structure to accommodate additional Mexican data
ArcGIS Online (AGOL) map development, integration and configuration |  | Update StoryMap text, all graphics, Tableau Dashboards, information cards, and 64 pdf documents manually by copying text from consolidated data sources in StoryMap components
Embed interactive data visualizations (graphs, tables)
Phase 3: Design \ Style | 35000 | Phase 3: Design \ Style | 10000
TxDOT Design Implementation: |  | Limited to StoryMap platform constraints
Extract and replicate navigation structure, header/footer, color scheme, typography |  | Meet accessibility requirements (currently no guidance for StoryMaps)
Reference TxDOT Brand Guidelines for official colors, logos, and standards
Meet TxDOT guidance for website accessibility requirements
Brand Alignment:
Verify alignment with TxDOT brand identity
Phase 4: Testing, QA and Deployment | 30000 | Phase 4: Testing/ QA | 45000
Cross-browser testing, PDF verification, and performance testing |  | Conduct rigorous QA/QC - Check data is consistent across StoryMap text, tableau, information cards, pdf documents, graphs and visualizations
Phase 5: Revisions \ Final Edits | 15000 | Phase 5: Revisions \ Final Edits | 20000
TxDOT review and feedback |  | TxDOT review and feedback
Final edits and quality assurance |  | Final edits and quality assurance
Cost Estimate | 200000 |  | 170000
Future updates only involves Phase 1 (partial) + 4 + 5 | 100000 | Future updates involves Phase 1 + 2 + 4 + 5 | 160000