## v1
Website Tasks | Timeframe | Cost
Phase 1: Data Preparation \ Content Migration | March to May | 65000
Design data architecture (CSV/Markdown) and migrate content from 2025 Bridge Guidebook PDFs
Update data as 2025 data becomes available
QA/QC CSV and Markdown files (No duplicated data across files)
Translate website text to allow for bilingual navigation
Phase 2: Core Development | April - July | 55000
Build scripts for web page and PDF generation (automation)
ArcGIS Online (AGOL) map development, integration and configuration
Embed interactive data visualizations (graphs, tables)
Phase 3: Design \ Style | May - July | 35000
TxDOT Design Implementation:
Extract and replicate navigation structure, header/footer, color scheme, typography
Reference TxDOT Brand Guidelines for official colors, logos, and standards
Meet TxDOT guidance for website accessibility requirements
Brand Alignment:
Verify alignment with TxDOT brand identity
Phase 4: Testing, QA and Deployment | May - July | 30000
Cross-browser testing, PDF verification, and performance testing
Phase 5: Revisions \ Final Edits | May - Aug | 15000
TxDOT review and feedback
Final edits and quality assurance
Cost Estimate |  | 200000