## v1
| Website (Hours) |  | StoryMap (Hours)
Phase 1: Data Preparation \ Content Migration |  | Phase 1: Data Preparation \ Content Migration
Structure data spreadsheets (CSV) and text document (Markdown) templates | 40 | Consolidate information in spreadsheets, PPT, and PDFs into fewer files to allow for data checking | 60
Migrate data from 2025 Bridge Guidebook PDFs and populate CSV and Markdown files | 40 | Update data as 2025 data becomes available | 120
Update data as 2025 data becomes available | 120
QA/QC CSV and Markdown files (No duplicated data across files) | 16
Phase 2: Foundation |  | Phase 2: Foundation
Build website architecture | 120 | Revise StoryMap structure to accommodate additional Mexican data | 40
Phase 3: Core Development |  | Phase 3: Core Development
Build scripts for web page and PDF generation (automation) | 80 | Update StoryMap text, all graphics, Tableau Dashboards, information cards, and 64 pdf documents manually by copying text from consolidated data sources in StoryMap components | 160
ArcGIS Online (AGOL) map integration and configuration | 40
Translate website text to allow for bilingual navigation and language switching | 40
Embed interactive data visualizations (graphs, tables) | 40
Phase 4: Design \ Style |  | Phase 4: Design \ Style
TxDOT Design Implementation: |  | Limited to StoryMap platform constraints
Extract and replicate navigation structure, header/footer, color scheme, typography ✓ Done — IBM Plex Sans, TxDOT brand colors implemented | 25 | Meet accessibility requirements (currently no guidance for StoryMaps | 40
Reference TxDOT Brand Guidelines for official colors, logos, and standards | 25
Meet TxDOT guidance for website accessibility requirements | 25
Brand Alignment:
Verify alignment with TxDOT brand identity | 32
Phase 5: Testing, QA \ Deployment |  | Phase 5: Testing, QA \ Deployment
Process testing with full dataset | 40 | Conduct rigorous QA/QC - Check data is consistent across StoryMap text, tableau, information cards, pdf documents, graphs and visualizations | 80
Cross-browser testing | 40
PDF quality verification | 8
Link checking and validation | 8
Performance testing | 8
Phase 6: Revisions \ Final Edits |  | Phase 6: Revisions \ Final Edits
TxDOT review and feedback |  | TxDOT review and feedback
Content adjustments and refinements | 20 | Content adjustments and refinements | 60
Final edits and quality assurance | 8 | Final edits and quality assurance | 60
Future updates only involves Phase 1 (update of data) and 6 (final checks before publishing) |  | Future updates involves Phase 1 (update of data), 3, 5, and 6 (final checks before publishing)

## v2
Website Tasks | Hours | StoryMap Tasks | Hours
Phase 1: Data Preparation \ Content Migration |  | Phase 1: Data Preparation \ Content Migration
Design data architecture (CSV/Markdown) and migrate content from 2025 Bridge Guidebook PDFs | 80 | Consolidate information in spreadsheets, PPT, and PDFs into fewer files to allow for data checking | 60
Update data as 2025 data becomes available | 120 | Update data as 2025 data becomes available | 120
QA/QC CSV and Markdown files (No duplicated data across files) | 16
Translate website text to allow for bilingual navigation | 80
Phase 2: Core Development |  | Phase 2: Core Development
Build scripts for web page and PDF generation (automation) | 80 | Revise StoryMap structure to accommodate additional Mexican data | 40
ArcGIS Online (AGOL) map development, integration and configuration | 80 | Update StoryMap text, all graphics, Tableau Dashboards, information cards, and 64 pdf documents manually by copying text from consolidated data sources in StoryMap components | 160
Embed interactive data visualizations (graphs, tables) | 80
Phase 3: Design \ Style |  | Phase 3: Design \ Style
TxDOT Design Implementation: |  | Limited to StoryMap platform constraints
Extract and replicate navigation structure, header/footer, color scheme, typography ✓ Done — IBM Plex Sans, TxDOT brand colors implemented | 16 | Meet accessibility requirements (currently no guidance for StoryMaps) | 40
Reference TxDOT Brand Guidelines for official colors, logos, and standards | 16
Meet TxDOT guidance for website accessibility requirements | 32
Brand Alignment:
Verify alignment with TxDOT brand identity | 20
Phase 4: Testing, QA and Deployment |  | Phase 4: Testing, QA and Deployment
Cross-browser testing, PDF verification, and performance testing | 90 | Conduct rigorous QA/QC - Check data is consistent across StoryMap text, tableau, information cards, pdf documents, graphs and visualizations | 80
Phase 5: Revisions \ Final Edits |  | Phase 5: Revisions \ Final Edits
TxDOT review and feedback |  | TxDOT review and feedback
Content adjustments and refinements | 25 | Content adjustments and refinements | 60
Final edits and quality assurance | 20 | Final edits and quality assurance | 60
Total Hours | 755 | Total Hours | 620
Future updates only involves Phase 1 + 4 + 5 = ~136 (data) + 90 (testing) + 40 (revisions) = ~266 hrs/cycle |  | Future updates involves Phase 1 + 2 + 4 + 5 = ~120 (data) + 200 (core dev) + 80 (testing) + 120 (revisions) = ~520 hrs/cy